## Master WBSGanttChart
Jonathan, Josh, and Jack
| Gantt Chart/WBS | JT | JB | JS
Task |  | Leader | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
Accelerometer
Initialization in board |  | Team
Detects when safe is moving |  | JS
Integrates with motor |  | JS
Integrates with LCD display |  | Team
Touch Switch
Resets the passcode |  | JT
Turns off alarm |  | JT
Numeric Keypad
Integrate with other sensors/switches |  | JB
Stores the values of set code |  | JB
Stepper Motor
Integration of motor |  | Team
Opens when correct input is put in |  | JS/JB
Locks the safe when closed |  | JB
Locks default |  | JS
Lock mechanism |  | JS/JB
Task |  | Leader | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
LCD
Shows passcode |  | JB
Shows failed attempts |  | JB
Shows when it is locked (after) |  | JT
Shows when safe is moving |  | JS
Shows when unlocked |  | JS
Project Integration
Build prototype - cube |  | Team
Integrate sensors/touch switch |  | Team
Hide the wires |  | Team
Implement the battery to safe |  | Team
Sleep mode until activated |  | Team
Project Management
Plan |  | JT
Meeting |  | JT
Report |  | JT/Team

## Design Update WBSGanttChart
This sheet is for Design Update, which will be screenshot and presented
Jonathan, Josh, and Jack
| Gantt Chart/WBS | JT | JB | JS
Task |  | Leader | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
Accelerometer
Initialization in board |  | Team
Detects when safe is moving |  | JS
Integrates with motor |  | JS
Integrates with LCD display |  | Team
Touch Switch
Resets the passcode |  | JT
Turns off alarm |  | JT
Numeric Keypad
Integrate with other sensors/switches |  | JB
Stores the values of set code |  | JB
Stepper Motor
Integration of motor |  | Team
Opens when correct input is put in |  | JS/JB
Locks the safe when closed |  | JB
Locks default |  | JS
Lock mechanism |  | JS/JB
Task |  | Leader | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
LCD
Shows passcode |  | JB
Shows failed attempts |  | JB
Shows when it is locked (after) |  | JT
Shows when safe is moving |  | JS
Shows when unlocked |  | JS
Project Integration
Build prototype - cube |  | Team
Integrate sensors/touch switch |  | Team
Hide the wires |  | Team
Implement the battery to safe |  | Team
Sleep mode until activated |  | Team
Project Management
Plan |  | JT
Meeting |  | JT
Report |  | JT/Team